## Optimization_Notes
Refinery Production Planning – Optimization Notes (Objective Function & Constraints)
Multi-period LP: 31 days (Oct 2026), 4 crudes, CDU → Reformer / RFCC / DHT, 10 tanks. Days 1–11 actual (locked), days 12–31 to optimise.
1. PURPOSE & WORKFLOW
This workbook is a test-bed for a Python optimizer. Excel holds the data, the current (manual) plan and all checks; Python reads the data, solves for the best plan, and writes the decision variables back into Daily_Plan. Excel then recalculates margins, tank balances and constraint checks so the optimizer result can be verified independently of the solver.
Step 1 | Read parameters: Crude_Data, Unit_Data, Product_Data, Tank_Master, Crude_Receipts, Product_Liftings.
Step 2 | Read Daily_Plan rows 5–35. Rows with Status = 'Actual' are fixed history; rows with Status = 'Plan' are free.
Step 3 | Build and solve the LP below (scipy.optimize.linprog / HiGHS, PuLP or Pyomo all work).
Step 4 | Write optimal x, r, f into Daily_Plan!D:I for Plan rows only (green cells).
Step 5 | Open in Excel → check Constraint_Check!X37 = 0 and compare Daily_Plan KPI 'Plan-days margin' against the benchmark in section 9.
2. COLOUR LEGEND
| Blue text, yellow fill | Parameter / input – edit to run scenarios
| Blue text, green fill | Decision variable – optimizer writes here (Daily_Plan Plan rows)
| Blue text, grey fill | Actual (locked) day – do not optimise
| Black text | Formula / calculation
| Green text | Link to another worksheet
3. SETS & INDICES
| Symbol | Meaning | Members / Excel source
| t ∈ T | Day of horizon | 1…31 (Daily_Plan col A). T_plan = days with Status 'Plan' (12…31)
| c ∈ C | Crude grade | Arab Light, Murban, Tapis, Kimanis (Crude_Data C3:F3)
| p ∈ P | Finished product | LPG, Naphtha, Gasoline 95, Jet A-1, Diesel B10, Fuel Oil (Product_Data C3:H3)
| k ∈ K | Tank | 4 crude tanks + 6 product tanks (Tank_Master A4:A13)
4. DECISION VARIABLES (per plan day t, units kbbl/d)
| Variable | Meaning | Excel location | Bounds
| x[c,t] | Crude c charged to the CDU | Daily_Plan!D:G | 0 … Xmax_c
| r[t] | SR naphtha routed to the Reformer (rest sold as Naphtha) | Daily_Plan!H | Rmin … Rmax
| f[t] | Atmospheric residue routed to the RFCC (rest goes to Fuel Oil) | Daily_Plan!I | Fmin … Fmax
| I[k,t] | Closing inventory of tank k (state variable, can be eliminated by substitution) | Tank_Balance!I | Min heel … Capacity
Total: 6 free variables × 20 plan days = 120 decision variables (+ 200 inventory states if modelled explicitly).
5. DERIVED FLOWS (all linear in x, r, f – see Daily_Plan formulas)
| Quantity | Expression | Excel column
| CDU_t | Σc x[c,t] | Daily_Plan!J
| Cut_j,t (j = LPG, Naph, Kero, GO, AR) | Σc y[c,j] · x[c,t] | Daily_Plan!K:O
| DHT_t | GO_t + yLCO · f[t] | Daily_Plan!W
| LPG_t | LPG_SR,t + yRef,LPG · r[t] + yFCC,LPG · f[t] | Daily_Plan!X
| Naphtha_t | Naph_t − r[t] | Daily_Plan!Y
| Gasoline_t | yRef,Reformate · r[t] + yFCC,Gasoline · f[t] | Daily_Plan!Z
| Jet_t | Kero_t | Daily_Plan!AA
| Diesel_t | yDHT · DHT_t | Daily_Plan!AB
| FuelOil_t | AR_t − f[t] + ySlurry · f[t] | Daily_Plan!AC
6. OBJECTIVE FUNCTION – maximise gross margin over plan days ($k)
max Z = Σ(t∈T_plan) [ Σp Price_p · Prod[p,t] − Σc CrudePrice_c · x[c,t] − ( OpexCDU · CDU_t + OpexRef · r[t] + OpexRFCC · f[t] + OpexDHT · DHT_t ) ]
| Term | Meaning | Excel source
| Revenue | Product make valued at netback price (production-based valuation) | Daily_Plan!AE ← Product_Data row 4
| Crude cost | Delivered crude price × crude charged | Daily_Plan!AF ← Crude_Data row 4
| Opex | Variable operating cost per bbl of unit feed | Daily_Plan!AG ← Unit_Data D7, D10, D16, D24
| Z | Plan-days gross margin (actual days are constant and excluded) | Daily_Plan KPI 'Plan-days margin'
Tip: because every product is linear in (x, r, f), the objective collapses to a constant margin coefficient per variable – e.g. Z = Σt (m_c · x[c,t] + m_r · r[t] + m_f · f[t]). Compute m from the Excel parameters; it shows instantly which crude/unit is most valuable and why the solver pushes against certain limits.
7. CONSTRAINTS (✓ = checked live in Constraint_Check)
ID | Constraint | Mathematical form (for every plan day t unless noted) | Parameter source | Type
C1 | CDU capacity / turndown | CDUmin ≤ Σc x[c,t] ≤ CDUmax | Unit_Data D4:D5 | Capacity ✓
C2 | Crude rate limits | Xmin_c ≤ x[c,t] ≤ Xmax_c | Crude_Data row 13–14 | Bound ✓
C3 | CDU ramp rate | −Ramp ≤ CDU_t − CDU_(t−1) ≤ Ramp (day 12 is linked to actual day 11) | Unit_Data D6 | Operability ✓
C4 | Reformer capacity | Rmin ≤ r[t] ≤ Rmax | Unit_Data D8:D9 | Capacity ✓
C5 | Naphtha availability | r[t] ≤ Σc yNaph,c · x[c,t] (Naphtha sales ≥ 0) | Crude_Data row 6 | Mass balance ✓
C6 | RFCC capacity | Fmin ≤ f[t] ≤ Fmax | Unit_Data D14:D15 | Capacity ✓
C7 | Residue availability | f[t] ≤ Σc yAR,c · x[c,t] (Fuel Oil ≥ 0) | Crude_Data row 9 | Mass balance ✓
C8 | DHT capacity | DHTmin ≤ Σc yGO,c · x[c,t] + yLCO · f[t] ≤ DHTmax | Unit_Data D22:D23 | Capacity ✓
C9 | Gasoline RON spec | (RONref − RONspec) · yRef · r[t] + (RONfcc − RONspec) · yFCC · f[t] ≥ 0 (linearised blend) | Unit_Data D26:D28 | Quality ✓
C10 | Residue sulfur spec | Σc yAR,c · (S_c − Smax) · x[c,t] ≤ 0 (linearised blend) | Crude_Data row 12, Unit_Data D29 | Quality ✓
C11 | Crude tank balance | I[c,t] = I[c,t−1] + Receipt[c,t] − x[c,t] | Crude_Receipts, Tank_Master F | Material balance
C12 | Product tank balance | I[p,t] = I[p,t−1] + Prod[p,t] − Lift[p,t] | Product_Liftings, Tank_Master F | Material balance
C13 | Tank operating window | MinHeel_k ≤ I[k,t] ≤ Capacity_k | Tank_Master D:E | Inventory ✓
C14 | End-of-month inventory | I[k,31] ≥ EndTarget_k | Tank_Master G | Inventory ✓
C15 | Lock actual days | x, r, f fixed at recorded values where Status = 'Actual' | Daily_Plan!C | Rolling horizon
C16 | Non-negativity | x, r, f, I ≥ 0 | - | Bound
Why C9 and C10 are linear: a ratio spec such as (Σ q_i·v_i)/(Σ v_i) ≥ spec is multiplied through by the (positive) pool volume, giving Σ (q_i − spec)·v_i ≥ 0. This keeps the whole model an LP – no NLP solver needed.
8. KEY ASSUMPTIONS & SIMPLIFICATIONS
• Fixed (linear) yields – no cut-point, severity or conversion optimisation. Upgrade path: delta-base vectors or swing cuts.
• Volumetric blending for RON and sulfur (sulfur should strictly be mass-weighted; acceptable for a test model).
• Products valued on production (netback); liftings and crude receipts are fixed schedules, so tanks absorb the imbalance.
• Crude and product tanks are aggregated per grade/product (one tank group each).
• Single day time-step; no unit shutdowns, catalyst cycle or maintenance windows modelled.
• All prices, yields and capacities are illustrative values for testing only.
9. BENCHMARK – use this to validate your Python optimizer
| Item | Value ($k) | How obtained
| Original manual plan – plan days 12–31 | 17024.9 | Daily_Plan values as delivered in this file
| Reference LP optimum – plan days 12–31 | 18320 | scipy.optimize.linprog (HiGHS), solved at file creation on the baseline data
| Reference uplift (optimum − original) | 1295.1 | Value of optimisation over 20 plan days
| Current plan in Daily_Plan – plan days | 17024.88 | Live – updates when the optimizer writes results
| Gap: LP optimum − current plan | 1295.12 | ≈ 0 when your optimizer matches the reference
A correct optimizer should reach ≈ 18,320 $k with Constraint_Check!X37 = 0. The LP optimum is degenerate (several plans give the same margin), so your crude split may differ from someone else's while the objective value matches. Typical binding constraints: CDU max, Reformer max, RFCC max, residue sulfur (C10), crude tank min-heel and end-of-month targets.

## Daily_Plan
Refinery Daily Production Plan – October 2026 (kbbl/d, $k/d)
Days 1–11 = ACTUAL (locked). Days 12–31 = PLAN. Green cells = decision variables the Python optimizer writes back; everything else is calculated.
|  |  | DECISION VARIABLES (kbbl/d) | [5 empty] | CDU – straight-run cuts | [6 empty] | Reformer |  | RFCC |  |  |  | DHT | Product make (kbbl/d) | [5 empty] | Quality | Economics ($k/d)
Day | Date | Status | Crude: Arab Light | Crude: Murban | Crude: Tapis | Crude: Kimanis | Reformer feed | RFCC feed | CDU total | SR LPG | SR Naphtha | SR Kerosene | SR Gasoil | Atm Residue | Residue S (wt%) | Reformate | Reformer LPG | FCC gasoline | FCC LPG | LCO | Slurry | DHT feed | LPG | Naphtha | Gasoline 95 | Jet A-1 | Diesel B10 | Fuel Oil | Gasoline RON | Product revenue | Crude cost | Opex | Gross margin | Margin $/bbl crude
1 | 2026-10-01 | Actual | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
2 | 2026-10-02 | Actual | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
3 | 2026-10-03 | Actual | 41 | 38 | 41 | 30 | 23 | 33 | 150 | 3.79 | 31.52 | 23.29 | 38.46 | 51.44 | 1.4698 | 19.32 | 1.84 | 17.16 | 5.94 | 5.94 | 1.98 | 44.4 | 11.57 | 8.52 | 36.48 | 23.29 | 43.512 | 20.42 | 95.1776 | 13374.07 | 12094 | 406.1 | 873.97 | 5.8265
4 | 2026-10-04 | Actual | 39 | 36 | 39 | 28 | 21 | 30 | 142 | 3.59 | 29.84 | 22.05 | 36.38 | 48.72 | 1.4742 | 17.64 | 1.68 | 15.6 | 5.4 | 5.4 | 1.8 | 41.78 | 10.67 | 8.84 | 33.24 | 22.05 | 40.9444 | 20.52 | 95.1841 | 12632.872 | 11448 | 377.17 | 807.702 | 5.688
5 | 2026-10-05 | Actual | 35 | 34 | 37 | 26 | 19 | 28 | 132 | 3.35 | 27.8 | 20.53 | 33.9 | 45.1 | 1.4487 | 15.96 | 1.52 | 14.56 | 5.04 | 5.04 | 1.68 | 38.94 | 9.91 | 8.8 | 30.52 | 20.53 | 38.1612 | 18.78 | 95.1376 | 11740.956 | 10650 | 349.91 | 741.046 | 5.614
6 | 2026-10-06 | Actual | 37 | 36 | 38 | 28 | 20 | 30 | 139 | 3.52 | 29.26 | 21.6 | 35.68 | 47.55 | 1.4528 | 16.8 | 1.6 | 15.6 | 5.4 | 5.4 | 1.8 | 41.08 | 10.52 | 9.26 | 32.4 | 21.6 | 40.2584 | 19.35 | 95.1111 | 12369.172 | 11212 | 370.62 | 786.552 | 5.6586
7 | 2026-10-07 | Actual | 39 | 38 | 40 | 30 | 22 | 32 | 147 | 3.72 | 30.94 | 22.84 | 37.76 | 50.27 | 1.4495 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 43.52 | 11.24 | 8.94 | 35.12 | 22.84 | 42.6496 | 20.19 | 95.1572 | 13097.248 | 11858 | 395.28 | 843.968 | 5.7413
8 | 2026-10-08 | Actual | 40 | 40 | 40 | 30 | 22 | 33 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 17.16 | 5.94 | 5.94 | 1.98 | 44.34 | 11.5 | 9.6 | 35.64 | 23.3 | 43.4532 | 20.38 | 95.1111 | 13358.606 | 12095 | 403.51 | 860.096 | 5.734
9 | 2026-10-09 | Actual | 40 | 40 | 41 | 29 | 23 | 33 | 150 | 3.81 | 31.62 | 23.32 | 38.38 | 51.37 | 1.4616 | 19.32 | 1.84 | 17.16 | 5.94 | 5.94 | 1.98 | 44.32 | 11.59 | 8.62 | 36.48 | 23.32 | 43.4336 | 20.35 | 95.1776 | 13372.488 | 12096.5 | 405.98 | 870.008 | 5.8001
10 | 2026-10-10 | Actual | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
11 | 2026-10-11 | Actual | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
12 | 2026-10-12 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
13 | 2026-10-13 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
14 | 2026-10-14 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
15 | 2026-10-15 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
16 | 2026-10-16 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
17 | 2026-10-17 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
18 | 2026-10-18 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
19 | 2026-10-19 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
20 | 2026-10-20 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
21 | 2026-10-21 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
22 | 2026-10-22 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
23 | 2026-10-23 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
24 | 2026-10-24 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
25 | 2026-10-25 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
26 | 2026-10-26 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
27 | 2026-10-27 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
28 | 2026-10-28 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
29 | 2026-10-29 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
30 | 2026-10-30 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
31 | 2026-10-31 | Plan | 40 | 40 | 40 | 30 | 22 | 32 | 150 | 3.8 | 31.6 | 23.3 | 38.4 | 51.4 | 1.4611 | 18.48 | 1.76 | 16.64 | 5.76 | 5.76 | 1.92 | 44.16 | 11.32 | 9.6 | 35.12 | 23.3 | 43.2768 | 21.32 | 95.1572 | 13345.484 | 12095 | 399.24 | 851.244 | 5.675
Month |  | Total | 1231 | 1222 | 1236 | 921 | 678 | 987 | 4610 | 116.78 | 970.98 | 716.13 | 1180.56 | 1579.45 | 1.4608 | 569.52 | 54.24 | 513.24 | 177.66 | 177.66 | 59.22 | 1358.22 | 348.68 | 292.98 | 1082.76 | 716.13 | 1331.0556 | 651.67 | 95.1558 | 410237.028 | 371733.5 | 12290.33 | 26213.198 | 5.6862
KPIs
Month gross margin ($k) | [5 empty] | 26213.198
Actual-days margin ($k) – locked | [5 empty] | 9188.318
Plan-days margin ($k) – OBJECTIVE | [5 empty] | 17024.88
Total crude run (kbbl) | [5 empty] | 4610
Constraint violations (from Constraint_Check) | [5 empty] | 0
Plan status | [5 empty] | FEASIBLE
Note on D4: Decision variables x[c,t]: crude c charged to CDU on day t (kbbl/d). Optimizer writes rows with Status = Plan only.
Note on H4: Decision variable r[t]: SR naphtha routed to Reformer. Remainder is sold as Naphtha.
Note on I4: Decision variable f[t]: Atm residue routed to RFCC. Remainder goes to Fuel Oil.

## Tank_Balance
Daily Tank Balance (kbbl) – long format, one row per tank per day
Closing = Opening + Inflow − Outflow. Crude: inflow = receipts, outflow = CDU charge. Product: inflow = production, outflow = liftings.
Tank ID | Service | Type | Day | Date | Opening | Inflow | Outflow | Closing | Min heel | Capacity | Status | Fill %
TK-101 | Arab Light | Crude | 1 | 2026-10-01 | 700 | 0 | 40 | 660 | 150 | 1500 | OK | 44%
TK-101 | Arab Light | Crude | 2 | 2026-10-02 | 660 | 0 | 40 | 620 | 150 | 1500 | OK | 41.33%
TK-101 | Arab Light | Crude | 3 | 2026-10-03 | 620 | 0 | 41 | 579 | 150 | 1500 | OK | 38.6%
TK-101 | Arab Light | Crude | 4 | 2026-10-04 | 579 | 0 | 39 | 540 | 150 | 1500 | OK | 36%
TK-101 | Arab Light | Crude | 5 | 2026-10-05 | 540 | 0 | 35 | 505 | 150 | 1500 | OK | 33.67%
TK-101 | Arab Light | Crude | 6 | 2026-10-06 | 505 | 0 | 37 | 468 | 150 | 1500 | OK | 31.2%
TK-101 | Arab Light | Crude | 7 | 2026-10-07 | 468 | 0 | 39 | 429 | 150 | 1500 | OK | 28.6%
TK-101 | Arab Light | Crude | 8 | 2026-10-08 | 429 | 600 | 40 | 989 | 150 | 1500 | OK | 65.93%
TK-101 | Arab Light | Crude | 9 | 2026-10-09 | 989 | 0 | 40 | 949 | 150 | 1500 | OK | 63.27%
TK-101 | Arab Light | Crude | 10 | 2026-10-10 | 949 | 0 | 40 | 909 | 150 | 1500 | OK | 60.6%
TK-101 | Arab Light | Crude | 11 | 2026-10-11 | 909 | 0 | 40 | 869 | 150 | 1500 | OK | 57.93%
TK-101 | Arab Light | Crude | 12 | 2026-10-12 | 869 | 0 | 40 | 829 | 150 | 1500 | OK | 55.27%
TK-101 | Arab Light | Crude | 13 | 2026-10-13 | 829 | 0 | 40 | 789 | 150 | 1500 | OK | 52.6%
TK-101 | Arab Light | Crude | 14 | 2026-10-14 | 789 | 0 | 40 | 749 | 150 | 1500 | OK | 49.93%
TK-101 | Arab Light | Crude | 15 | 2026-10-15 | 749 | 0 | 40 | 709 | 150 | 1500 | OK | 47.27%
TK-101 | Arab Light | Crude | 16 | 2026-10-16 | 709 | 0 | 40 | 669 | 150 | 1500 | OK | 44.6%
TK-101 | Arab Light | Crude | 17 | 2026-10-17 | 669 | 0 | 40 | 629 | 150 | 1500 | OK | 41.93%
TK-101 | Arab Light | Crude | 18 | 2026-10-18 | 629 | 0 | 40 | 589 | 150 | 1500 | OK | 39.27%
TK-101 | Arab Light | Crude | 19 | 2026-10-19 | 589 | 0 | 40 | 549 | 150 | 1500 | OK | 36.6%
TK-101 | Arab Light | Crude | 20 | 2026-10-20 | 549 | 0 | 40 | 509 | 150 | 1500 | OK | 33.93%
TK-101 | Arab Light | Crude | 21 | 2026-10-21 | 509 | 0 | 40 | 469 | 150 | 1500 | OK | 31.27%
TK-101 | Arab Light | Crude | 22 | 2026-10-22 | 469 | 500 | 40 | 929 | 150 | 1500 | OK | 61.93%
TK-101 | Arab Light | Crude | 23 | 2026-10-23 | 929 | 0 | 40 | 889 | 150 | 1500 | OK | 59.27%
TK-101 | Arab Light | Crude | 24 | 2026-10-24 | 889 | 0 | 40 | 849 | 150 | 1500 | OK | 56.6%
TK-101 | Arab Light | Crude | 25 | 2026-10-25 | 849 | 0 | 40 | 809 | 150 | 1500 | OK | 53.93%
TK-101 | Arab Light | Crude | 26 | 2026-10-26 | 809 | 0 | 40 | 769 | 150 | 1500 | OK | 51.27%
TK-101 | Arab Light | Crude | 27 | 2026-10-27 | 769 | 0 | 40 | 729 | 150 | 1500 | OK | 48.6%
TK-101 | Arab Light | Crude | 28 | 2026-10-28 | 729 | 0 | 40 | 689 | 150 | 1500 | OK | 45.93%
TK-101 | Arab Light | Crude | 29 | 2026-10-29 | 689 | 0 | 40 | 649 | 150 | 1500 | OK | 43.27%
TK-101 | Arab Light | Crude | 30 | 2026-10-30 | 649 | 0 | 40 | 609 | 150 | 1500 | OK | 40.6%
TK-101 | Arab Light | Crude | 31 | 2026-10-31 | 609 | 0 | 40 | 569 | 150 | 1500 | OK | 37.93%
TK-102 | Murban | Crude | 1 | 2026-10-01 | 500 | 0 | 40 | 460 | 100 | 1000 | OK | 46%
TK-102 | Murban | Crude | 2 | 2026-10-02 | 460 | 0 | 40 | 420 | 100 | 1000 | OK | 42%
TK-102 | Murban | Crude | 3 | 2026-10-03 | 420 | 0 | 38 | 382 | 100 | 1000 | OK | 38.2%
TK-102 | Murban | Crude | 4 | 2026-10-04 | 382 | 0 | 36 | 346 | 100 | 1000 | OK | 34.6%
TK-102 | Murban | Crude | 5 | 2026-10-05 | 346 | 500 | 34 | 812 | 100 | 1000 | OK | 81.2%
TK-102 | Murban | Crude | 6 | 2026-10-06 | 812 | 0 | 36 | 776 | 100 | 1000 | OK | 77.6%
TK-102 | Murban | Crude | 7 | 2026-10-07 | 776 | 0 | 38 | 738 | 100 | 1000 | OK | 73.8%
TK-102 | Murban | Crude | 8 | 2026-10-08 | 738 | 0 | 40 | 698 | 100 | 1000 | OK | 69.8%
TK-102 | Murban | Crude | 9 | 2026-10-09 | 698 | 0 | 40 | 658 | 100 | 1000 | OK | 65.8%
TK-102 | Murban | Crude | 10 | 2026-10-10 | 658 | 0 | 40 | 618 | 100 | 1000 | OK | 61.8%
TK-102 | Murban | Crude | 11 | 2026-10-11 | 618 | 0 | 40 | 578 | 100 | 1000 | OK | 57.8%
TK-102 | Murban | Crude | 12 | 2026-10-12 | 578 | 0 | 40 | 538 | 100 | 1000 | OK | 53.8%
TK-102 | Murban | Crude | 13 | 2026-10-13 | 538 | 0 | 40 | 498 | 100 | 1000 | OK | 49.8%
TK-102 | Murban | Crude | 14 | 2026-10-14 | 498 | 0 | 40 | 458 | 100 | 1000 | OK | 45.8%
TK-102 | Murban | Crude | 15 | 2026-10-15 | 458 | 0 | 40 | 418 | 100 | 1000 | OK | 41.8%
TK-102 | Murban | Crude | 16 | 2026-10-16 | 418 | 0 | 40 | 378 | 100 | 1000 | OK | 37.8%
TK-102 | Murban | Crude | 17 | 2026-10-17 | 378 | 0 | 40 | 338 | 100 | 1000 | OK | 33.8%
TK-102 | Murban | Crude | 18 | 2026-10-18 | 338 | 0 | 40 | 298 | 100 | 1000 | OK | 29.8%
TK-102 | Murban | Crude | 19 | 2026-10-19 | 298 | 500 | 40 | 758 | 100 | 1000 | OK | 75.8%
TK-102 | Murban | Crude | 20 | 2026-10-20 | 758 | 0 | 40 | 718 | 100 | 1000 | OK | 71.8%
TK-102 | Murban | Crude | 21 | 2026-10-21 | 718 | 0 | 40 | 678 | 100 | 1000 | OK | 67.8%
TK-102 | Murban | Crude | 22 | 2026-10-22 | 678 | 0 | 40 | 638 | 100 | 1000 | OK | 63.8%
TK-102 | Murban | Crude | 23 | 2026-10-23 | 638 | 0 | 40 | 598 | 100 | 1000 | OK | 59.8%
TK-102 | Murban | Crude | 24 | 2026-10-24 | 598 | 0 | 40 | 558 | 100 | 1000 | OK | 55.8%
TK-102 | Murban | Crude | 25 | 2026-10-25 | 558 | 0 | 40 | 518 | 100 | 1000 | OK | 51.8%
TK-102 | Murban | Crude | 26 | 2026-10-26 | 518 | 0 | 40 | 478 | 100 | 1000 | OK | 47.8%
TK-102 | Murban | Crude | 27 | 2026-10-27 | 478 | 0 | 40 | 438 | 100 | 1000 | OK | 43.8%
TK-102 | Murban | Crude | 28 | 2026-10-28 | 438 | 0 | 40 | 398 | 100 | 1000 | OK | 39.8%
TK-102 | Murban | Crude | 29 | 2026-10-29 | 398 | 0 | 40 | 358 | 100 | 1000 | OK | 35.8%
TK-102 | Murban | Crude | 30 | 2026-10-30 | 358 | 0 | 40 | 318 | 100 | 1000 | OK | 31.8%
TK-102 | Murban | Crude | 31 | 2026-10-31 | 318 | 0 | 40 | 278 | 100 | 1000 | OK | 27.8%
TK-103 | Tapis | Crude | 1 | 2026-10-01 | 450 | 0 | 40 | 410 | 90 | 900 | OK | 45.56%
TK-103 | Tapis | Crude | 2 | 2026-10-02 | 410 | 0 | 40 | 370 | 90 | 900 | OK | 41.11%
TK-103 | Tapis | Crude | 3 | 2026-10-03 | 370 | 0 | 41 | 329 | 90 | 900 | OK | 36.56%
TK-103 | Tapis | Crude | 4 | 2026-10-04 | 329 | 0 | 39 | 290 | 90 | 900 | OK | 32.22%
TK-103 | Tapis | Crude | 5 | 2026-10-05 | 290 | 0 | 37 | 253 | 90 | 900 | OK | 28.11%
TK-103 | Tapis | Crude | 6 | 2026-10-06 | 253 | 400 | 38 | 615 | 90 | 900 | OK | 68.33%
TK-103 | Tapis | Crude | 7 | 2026-10-07 | 615 | 0 | 40 | 575 | 90 | 900 | OK | 63.89%
TK-103 | Tapis | Crude | 8 | 2026-10-08 | 575 | 0 | 40 | 535 | 90 | 900 | OK | 59.44%
TK-103 | Tapis | Crude | 9 | 2026-10-09 | 535 | 0 | 41 | 494 | 90 | 900 | OK | 54.89%
TK-103 | Tapis | Crude | 10 | 2026-10-10 | 494 | 0 | 40 | 454 | 90 | 900 | OK | 50.44%
TK-103 | Tapis | Crude | 11 | 2026-10-11 | 454 | 0 | 40 | 414 | 90 | 900 | OK | 46%
TK-103 | Tapis | Crude | 12 | 2026-10-12 | 414 | 0 | 40 | 374 | 90 | 900 | OK | 41.56%
TK-103 | Tapis | Crude | 13 | 2026-10-13 | 374 | 0 | 40 | 334 | 90 | 900 | OK | 37.11%
TK-103 | Tapis | Crude | 14 | 2026-10-14 | 334 | 0 | 40 | 294 | 90 | 900 | OK | 32.67%
TK-103 | Tapis | Crude | 15 | 2026-10-15 | 294 | 0 | 40 | 254 | 90 | 900 | OK | 28.22%
TK-103 | Tapis | Crude | 16 | 2026-10-16 | 254 | 400 | 40 | 614 | 90 | 900 | OK | 68.22%
TK-103 | Tapis | Crude | 17 | 2026-10-17 | 614 | 0 | 40 | 574 | 90 | 900 | OK | 63.78%
TK-103 | Tapis | Crude | 18 | 2026-10-18 | 574 | 0 | 40 | 534 | 90 | 900 | OK | 59.33%
TK-103 | Tapis | Crude | 19 | 2026-10-19 | 534 | 0 | 40 | 494 | 90 | 900 | OK | 54.89%
TK-103 | Tapis | Crude | 20 | 2026-10-20 | 494 | 0 | 40 | 454 | 90 | 900 | OK | 50.44%
TK-103 | Tapis | Crude | 21 | 2026-10-21 | 454 | 0 | 40 | 414 | 90 | 900 | OK | 46%
TK-103 | Tapis | Crude | 22 | 2026-10-22 | 414 | 0 | 40 | 374 | 90 | 900 | OK | 41.56%
TK-103 | Tapis | Crude | 23 | 2026-10-23 | 374 | 0 | 40 | 334 | 90 | 900 | OK | 37.11%
TK-103 | Tapis | Crude | 24 | 2026-10-24 | 334 | 0 | 40 | 294 | 90 | 900 | OK | 32.67%
TK-103 | Tapis | Crude | 25 | 2026-10-25 | 294 | 0 | 40 | 254 | 90 | 900 | OK | 28.22%
TK-103 | Tapis | Crude | 26 | 2026-10-26 | 254 | 400 | 40 | 614 | 90 | 900 | OK | 68.22%
TK-103 | Tapis | Crude | 27 | 2026-10-27 | 614 | 0 | 40 | 574 | 90 | 900 | OK | 63.78%
TK-103 | Tapis | Crude | 28 | 2026-10-28 | 574 | 0 | 40 | 534 | 90 | 900 | OK | 59.33%
TK-103 | Tapis | Crude | 29 | 2026-10-29 | 534 | 0 | 40 | 494 | 90 | 900 | OK | 54.89%
TK-103 | Tapis | Crude | 30 | 2026-10-30 | 494 | 0 | 40 | 454 | 90 | 900 | OK | 50.44%
TK-103 | Tapis | Crude | 31 | 2026-10-31 | 454 | 0 | 40 | 414 | 90 | 900 | OK | 46%
TK-104 | Kimanis | Crude | 1 | 2026-10-01 | 380 | 0 | 30 | 350 | 80 | 800 | OK | 43.75%
TK-104 | Kimanis | Crude | 2 | 2026-10-02 | 350 | 0 | 30 | 320 | 80 | 800 | OK | 40%
TK-104 | Kimanis | Crude | 3 | 2026-10-03 | 320 | 0 | 30 | 290 | 80 | 800 | OK | 36.25%
TK-104 | Kimanis | Crude | 4 | 2026-10-04 | 290 | 0 | 28 | 262 | 80 | 800 | OK | 32.75%
TK-104 | Kimanis | Crude | 5 | 2026-10-05 | 262 | 0 | 26 | 236 | 80 | 800 | OK | 29.5%
TK-104 | Kimanis | Crude | 6 | 2026-10-06 | 236 | 0 | 28 | 208 | 80 | 800 | OK | 26%
TK-104 | Kimanis | Crude | 7 | 2026-10-07 | 208 | 0 | 30 | 178 | 80 | 800 | OK | 22.25%
TK-104 | Kimanis | Crude | 8 | 2026-10-08 | 178 | 0 | 30 | 148 | 80 | 800 | OK | 18.5%
TK-104 | Kimanis | Crude | 9 | 2026-10-09 | 148 | 0 | 29 | 119 | 80 | 800 | OK | 14.88%
TK-104 | Kimanis | Crude | 10 | 2026-10-10 | 119 | 350 | 30 | 439 | 80 | 800 | OK | 54.87%
TK-104 | Kimanis | Crude | 11 | 2026-10-11 | 439 | 0 | 30 | 409 | 80 | 800 | OK | 51.12%
TK-104 | Kimanis | Crude | 12 | 2026-10-12 | 409 | 0 | 30 | 379 | 80 | 800 | OK | 47.38%
TK-104 | Kimanis | Crude | 13 | 2026-10-13 | 379 | 0 | 30 | 349 | 80 | 800 | OK | 43.62%
TK-104 | Kimanis | Crude | 14 | 2026-10-14 | 349 | 0 | 30 | 319 | 80 | 800 | OK | 39.88%
TK-104 | Kimanis | Crude | 15 | 2026-10-15 | 319 | 0 | 30 | 289 | 80 | 800 | OK | 36.12%
TK-104 | Kimanis | Crude | 16 | 2026-10-16 | 289 | 0 | 30 | 259 | 80 | 800 | OK | 32.38%
TK-104 | Kimanis | Crude | 17 | 2026-10-17 | 259 | 0 | 30 | 229 | 80 | 800 | OK | 28.62%
TK-104 | Kimanis | Crude | 18 | 2026-10-18 | 229 | 0 | 30 | 199 | 80 | 800 | OK | 24.88%
TK-104 | Kimanis | Crude | 19 | 2026-10-19 | 199 | 0 | 30 | 169 | 80 | 800 | OK | 21.12%
TK-104 | Kimanis | Crude | 20 | 2026-10-20 | 169 | 0 | 30 | 139 | 80 | 800 | OK | 17.38%
TK-104 | Kimanis | Crude | 21 | 2026-10-21 | 139 | 0 | 30 | 109 | 80 | 800 | OK | 13.63%
TK-104 | Kimanis | Crude | 22 | 2026-10-22 | 109 | 350 | 30 | 429 | 80 | 800 | OK | 53.62%
TK-104 | Kimanis | Crude | 23 | 2026-10-23 | 429 | 0 | 30 | 399 | 80 | 800 | OK | 49.88%
TK-104 | Kimanis | Crude | 24 | 2026-10-24 | 399 | 0 | 30 | 369 | 80 | 800 | OK | 46.12%
TK-104 | Kimanis | Crude | 25 | 2026-10-25 | 369 | 0 | 30 | 339 | 80 | 800 | OK | 42.38%
TK-104 | Kimanis | Crude | 26 | 2026-10-26 | 339 | 0 | 30 | 309 | 80 | 800 | OK | 38.62%
TK-104 | Kimanis | Crude | 27 | 2026-10-27 | 309 | 0 | 30 | 279 | 80 | 800 | OK | 34.88%
TK-104 | Kimanis | Crude | 28 | 2026-10-28 | 279 | 0 | 30 | 249 | 80 | 800 | OK | 31.13%
TK-104 | Kimanis | Crude | 29 | 2026-10-29 | 249 | 0 | 30 | 219 | 80 | 800 | OK | 27.38%
TK-104 | Kimanis | Crude | 30 | 2026-10-30 | 219 | 0 | 30 | 189 | 80 | 800 | OK | 23.62%
TK-104 | Kimanis | Crude | 31 | 2026-10-31 | 189 | 0 | 30 | 159 | 80 | 800 | OK | 19.88%
TK-201 | LPG | Product | 1 | 2026-10-01 | 30 | 11.32 | 9 | 32.32 | 6 | 60 | OK | 53.87%
TK-201 | LPG | Product | 2 | 2026-10-02 | 32.32 | 11.32 | 9 | 34.64 | 6 | 60 | OK | 57.73%
TK-201 | LPG | Product | 3 | 2026-10-03 | 34.64 | 11.57 | 9 | 37.21 | 6 | 60 | OK | 62.02%
TK-201 | LPG | Product | 4 | 2026-10-04 | 37.21 | 10.67 | 9 | 38.88 | 6 | 60 | OK | 64.8%
TK-201 | LPG | Product | 5 | 2026-10-05 | 38.88 | 9.91 | 9 | 39.79 | 6 | 60 | OK | 66.32%
TK-201 | LPG | Product | 6 | 2026-10-06 | 39.79 | 10.52 | 9 | 41.31 | 6 | 60 | OK | 68.85%
TK-201 | LPG | Product | 7 | 2026-10-07 | 41.31 | 11.24 | 9 | 43.55 | 6 | 60 | OK | 72.58%
TK-201 | LPG | Product | 8 | 2026-10-08 | 43.55 | 11.5 | 9 | 46.05 | 6 | 60 | OK | 76.75%
TK-201 | LPG | Product | 9 | 2026-10-09 | 46.05 | 11.59 | 9 | 48.64 | 6 | 60 | OK | 81.07%
TK-201 | LPG | Product | 10 | 2026-10-10 | 48.64 | 11.32 | 39 | 20.96 | 6 | 60 | OK | 34.93%
TK-201 | LPG | Product | 11 | 2026-10-11 | 20.96 | 11.32 | 9 | 23.28 | 6 | 60 | OK | 38.8%
TK-201 | LPG | Product | 12 | 2026-10-12 | 23.28 | 11.32 | 9 | 25.6 | 6 | 60 | OK | 42.67%
TK-201 | LPG | Product | 13 | 2026-10-13 | 25.6 | 11.32 | 9 | 27.92 | 6 | 60 | OK | 46.53%
TK-201 | LPG | Product | 14 | 2026-10-14 | 27.92 | 11.32 | 9 | 30.24 | 6 | 60 | OK | 50.4%
TK-201 | LPG | Product | 15 | 2026-10-15 | 30.24 | 11.32 | 9 | 32.56 | 6 | 60 | OK | 54.27%
TK-201 | LPG | Product | 16 | 2026-10-16 | 32.56 | 11.32 | 9 | 34.88 | 6 | 60 | OK | 58.13%
TK-201 | LPG | Product | 17 | 2026-10-17 | 34.88 | 11.32 | 9 | 37.2 | 6 | 60 | OK | 62%
TK-201 | LPG | Product | 18 | 2026-10-18 | 37.2 | 11.32 | 9 | 39.52 | 6 | 60 | OK | 65.87%
TK-201 | LPG | Product | 19 | 2026-10-19 | 39.52 | 11.32 | 9 | 41.84 | 6 | 60 | OK | 69.73%
TK-201 | LPG | Product | 20 | 2026-10-20 | 41.84 | 11.32 | 9 | 44.16 | 6 | 60 | OK | 73.6%
TK-201 | LPG | Product | 21 | 2026-10-21 | 44.16 | 11.32 | 9 | 46.48 | 6 | 60 | OK | 77.47%
TK-201 | LPG | Product | 22 | 2026-10-22 | 46.48 | 11.32 | 9 | 48.8 | 6 | 60 | OK | 81.33%
TK-201 | LPG | Product | 23 | 2026-10-23 | 48.8 | 11.32 | 9 | 51.12 | 6 | 60 | OK | 85.2%
TK-201 | LPG | Product | 24 | 2026-10-24 | 51.12 | 11.32 | 39 | 23.44 | 6 | 60 | OK | 39.07%
TK-201 | LPG | Product | 25 | 2026-10-25 | 23.44 | 11.32 | 9 | 25.76 | 6 | 60 | OK | 42.93%
TK-201 | LPG | Product | 26 | 2026-10-26 | 25.76 | 11.32 | 9 | 28.08 | 6 | 60 | OK | 46.8%
TK-201 | LPG | Product | 27 | 2026-10-27 | 28.08 | 11.32 | 9 | 30.4 | 6 | 60 | OK | 50.67%
TK-201 | LPG | Product | 28 | 2026-10-28 | 30.4 | 11.32 | 9 | 32.72 | 6 | 60 | OK | 54.53%
TK-201 | LPG | Product | 29 | 2026-10-29 | 32.72 | 11.32 | 9 | 35.04 | 6 | 60 | OK | 58.4%
TK-201 | LPG | Product | 30 | 2026-10-30 | 35.04 | 11.32 | 9 | 37.36 | 6 | 60 | OK | 62.27%
TK-201 | LPG | Product | 31 | 2026-10-31 | 37.36 | 11.32 | 9 | 39.68 | 6 | 60 | OK | 66.13%
TK-301 | Naphtha | Product | 1 | 2026-10-01 | 110 | 9.6 | 0 | 119.6 | 25 | 250 | OK | 47.84%
TK-301 | Naphtha | Product | 2 | 2026-10-02 | 119.6 | 9.6 | 0 | 129.2 | 25 | 250 | OK | 51.68%
TK-301 | Naphtha | Product | 3 | 2026-10-03 | 129.2 | 8.52 | 0 | 137.72 | 25 | 250 | OK | 55.09%
TK-301 | Naphtha | Product | 4 | 2026-10-04 | 137.72 | 8.84 | 0 | 146.56 | 25 | 250 | OK | 58.62%
TK-301 | Naphtha | Product | 5 | 2026-10-05 | 146.56 | 8.8 | 0 | 155.36 | 25 | 250 | OK | 62.14%
TK-301 | Naphtha | Product | 6 | 2026-10-06 | 155.36 | 9.26 | 0 | 164.62 | 25 | 250 | OK | 65.85%
TK-301 | Naphtha | Product | 7 | 2026-10-07 | 164.62 | 8.94 | 0 | 173.56 | 25 | 250 | OK | 69.42%
TK-301 | Naphtha | Product | 8 | 2026-10-08 | 173.56 | 9.6 | 0 | 183.16 | 25 | 250 | OK | 73.26%
TK-301 | Naphtha | Product | 9 | 2026-10-09 | 183.16 | 8.62 | 100 | 91.78 | 25 | 250 | OK | 36.71%
TK-301 | Naphtha | Product | 10 | 2026-10-10 | 91.78 | 9.6 | 0 | 101.38 | 25 | 250 | OK | 40.55%
TK-301 | Naphtha | Product | 11 | 2026-10-11 | 101.38 | 9.6 | 0 | 110.98 | 25 | 250 | OK | 44.39%
TK-301 | Naphtha | Product | 12 | 2026-10-12 | 110.98 | 9.6 | 0 | 120.58 | 25 | 250 | OK | 48.23%
TK-301 | Naphtha | Product | 13 | 2026-10-13 | 120.58 | 9.6 | 0 | 130.18 | 25 | 250 | OK | 52.07%
TK-301 | Naphtha | Product | 14 | 2026-10-14 | 130.18 | 9.6 | 0 | 139.78 | 25 | 250 | OK | 55.91%
TK-301 | Naphtha | Product | 15 | 2026-10-15 | 139.78 | 9.6 | 0 | 149.38 | 25 | 250 | OK | 59.75%
TK-301 | Naphtha | Product | 16 | 2026-10-16 | 149.38 | 9.6 | 0 | 158.98 | 25 | 250 | OK | 63.59%
TK-301 | Naphtha | Product | 17 | 2026-10-17 | 158.98 | 9.6 | 0 | 168.58 | 25 | 250 | OK | 67.43%
TK-301 | Naphtha | Product | 18 | 2026-10-18 | 168.58 | 9.6 | 0 | 178.18 | 25 | 250 | OK | 71.27%
TK-301 | Naphtha | Product | 19 | 2026-10-19 | 178.18 | 9.6 | 0 | 187.78 | 25 | 250 | OK | 75.11%
TK-301 | Naphtha | Product | 20 | 2026-10-20 | 187.78 | 9.6 | 100 | 97.38 | 25 | 250 | OK | 38.95%
TK-301 | Naphtha | Product | 21 | 2026-10-21 | 97.38 | 9.6 | 0 | 106.98 | 25 | 250 | OK | 42.79%
TK-301 | Naphtha | Product | 22 | 2026-10-22 | 106.98 | 9.6 | 0 | 116.58 | 25 | 250 | OK | 46.63%
TK-301 | Naphtha | Product | 23 | 2026-10-23 | 116.58 | 9.6 | 0 | 126.18 | 25 | 250 | OK | 50.47%
TK-301 | Naphtha | Product | 24 | 2026-10-24 | 126.18 | 9.6 | 0 | 135.78 | 25 | 250 | OK | 54.31%
TK-301 | Naphtha | Product | 25 | 2026-10-25 | 135.78 | 9.6 | 0 | 145.38 | 25 | 250 | OK | 58.15%
TK-301 | Naphtha | Product | 26 | 2026-10-26 | 145.38 | 9.6 | 0 | 154.98 | 25 | 250 | OK | 61.99%
TK-301 | Naphtha | Product | 27 | 2026-10-27 | 154.98 | 9.6 | 0 | 164.58 | 25 | 250 | OK | 65.83%
TK-301 | Naphtha | Product | 28 | 2026-10-28 | 164.58 | 9.6 | 0 | 174.18 | 25 | 250 | OK | 69.67%
TK-301 | Naphtha | Product | 29 | 2026-10-29 | 174.18 | 9.6 | 0 | 183.78 | 25 | 250 | OK | 73.51%
TK-301 | Naphtha | Product | 30 | 2026-10-30 | 183.78 | 9.6 | 100 | 93.38 | 25 | 250 | OK | 37.35%
TK-301 | Naphtha | Product | 31 | 2026-10-31 | 93.38 | 9.6 | 0 | 102.98 | 25 | 250 | OK | 41.19%
TK-401 | Gasoline 95 | Product | 1 | 2026-10-01 | 180 | 35.12 | 30 | 185.12 | 40 | 400 | OK | 46.28%
TK-401 | Gasoline 95 | Product | 2 | 2026-10-02 | 185.12 | 35.12 | 30 | 190.24 | 40 | 400 | OK | 47.56%
TK-401 | Gasoline 95 | Product | 3 | 2026-10-03 | 190.24 | 36.48 | 30 | 196.72 | 40 | 400 | OK | 49.18%
TK-401 | Gasoline 95 | Product | 4 | 2026-10-04 | 196.72 | 33.24 | 30 | 199.96 | 40 | 400 | OK | 49.99%
TK-401 | Gasoline 95 | Product | 5 | 2026-10-05 | 199.96 | 30.52 | 30 | 200.48 | 40 | 400 | OK | 50.12%
TK-401 | Gasoline 95 | Product | 6 | 2026-10-06 | 200.48 | 32.4 | 30 | 202.88 | 40 | 400 | OK | 50.72%
TK-401 | Gasoline 95 | Product | 7 | 2026-10-07 | 202.88 | 35.12 | 30 | 208 | 40 | 400 | OK | 52%
TK-401 | Gasoline 95 | Product | 8 | 2026-10-08 | 208 | 35.64 | 30 | 213.64 | 40 | 400 | OK | 53.41%
TK-401 | Gasoline 95 | Product | 9 | 2026-10-09 | 213.64 | 36.48 | 30 | 220.12 | 40 | 400 | OK | 55.03%
TK-401 | Gasoline 95 | Product | 10 | 2026-10-10 | 220.12 | 35.12 | 30 | 225.24 | 40 | 400 | OK | 56.31%
TK-401 | Gasoline 95 | Product | 11 | 2026-10-11 | 225.24 | 35.12 | 30 | 230.36 | 40 | 400 | OK | 57.59%
TK-401 | Gasoline 95 | Product | 12 | 2026-10-12 | 230.36 | 35.12 | 110 | 155.48 | 40 | 400 | OK | 38.87%
TK-401 | Gasoline 95 | Product | 13 | 2026-10-13 | 155.48 | 35.12 | 30 | 160.6 | 40 | 400 | OK | 40.15%
TK-401 | Gasoline 95 | Product | 14 | 2026-10-14 | 160.6 | 35.12 | 30 | 165.72 | 40 | 400 | OK | 41.43%
TK-401 | Gasoline 95 | Product | 15 | 2026-10-15 | 165.72 | 35.12 | 30 | 170.84 | 40 | 400 | OK | 42.71%
TK-401 | Gasoline 95 | Product | 16 | 2026-10-16 | 170.84 | 35.12 | 30 | 175.96 | 40 | 400 | OK | 43.99%
TK-401 | Gasoline 95 | Product | 17 | 2026-10-17 | 175.96 | 35.12 | 30 | 181.08 | 40 | 400 | OK | 45.27%
TK-401 | Gasoline 95 | Product | 18 | 2026-10-18 | 181.08 | 35.12 | 30 | 186.2 | 40 | 400 | OK | 46.55%
TK-401 | Gasoline 95 | Product | 19 | 2026-10-19 | 186.2 | 35.12 | 30 | 191.32 | 40 | 400 | OK | 47.83%
TK-401 | Gasoline 95 | Product | 20 | 2026-10-20 | 191.32 | 35.12 | 30 | 196.44 | 40 | 400 | OK | 49.11%
TK-401 | Gasoline 95 | Product | 21 | 2026-10-21 | 196.44 | 35.12 | 30 | 201.56 | 40 | 400 | OK | 50.39%
TK-401 | Gasoline 95 | Product | 22 | 2026-10-22 | 201.56 | 35.12 | 30 | 206.68 | 40 | 400 | OK | 51.67%
TK-401 | Gasoline 95 | Product | 23 | 2026-10-23 | 206.68 | 35.12 | 30 | 211.8 | 40 | 400 | OK | 52.95%
TK-401 | Gasoline 95 | Product | 24 | 2026-10-24 | 211.8 | 35.12 | 30 | 216.92 | 40 | 400 | OK | 54.23%
TK-401 | Gasoline 95 | Product | 25 | 2026-10-25 | 216.92 | 35.12 | 30 | 222.04 | 40 | 400 | OK | 55.51%
TK-401 | Gasoline 95 | Product | 26 | 2026-10-26 | 222.04 | 35.12 | 110 | 147.16 | 40 | 400 | OK | 36.79%
TK-401 | Gasoline 95 | Product | 27 | 2026-10-27 | 147.16 | 35.12 | 30 | 152.28 | 40 | 400 | OK | 38.07%
TK-401 | Gasoline 95 | Product | 28 | 2026-10-28 | 152.28 | 35.12 | 30 | 157.4 | 40 | 400 | OK | 39.35%
TK-401 | Gasoline 95 | Product | 29 | 2026-10-29 | 157.4 | 35.12 | 30 | 162.52 | 40 | 400 | OK | 40.63%
TK-401 | Gasoline 95 | Product | 30 | 2026-10-30 | 162.52 | 35.12 | 30 | 167.64 | 40 | 400 | OK | 41.91%
TK-401 | Gasoline 95 | Product | 31 | 2026-10-31 | 167.64 | 35.12 | 30 | 172.76 | 40 | 400 | OK | 43.19%
TK-501 | Jet A-1 | Product | 1 | 2026-10-01 | 140 | 23.3 | 18 | 145.3 | 30 | 300 | OK | 48.43%
TK-501 | Jet A-1 | Product | 2 | 2026-10-02 | 145.3 | 23.3 | 18 | 150.6 | 30 | 300 | OK | 50.2%
TK-501 | Jet A-1 | Product | 3 | 2026-10-03 | 150.6 | 23.29 | 18 | 155.89 | 30 | 300 | OK | 51.96%
TK-501 | Jet A-1 | Product | 4 | 2026-10-04 | 155.89 | 22.05 | 18 | 159.94 | 30 | 300 | OK | 53.31%
TK-501 | Jet A-1 | Product | 5 | 2026-10-05 | 159.94 | 20.53 | 18 | 162.47 | 30 | 300 | OK | 54.16%
TK-501 | Jet A-1 | Product | 6 | 2026-10-06 | 162.47 | 21.6 | 18 | 166.07 | 30 | 300 | OK | 55.36%
TK-501 | Jet A-1 | Product | 7 | 2026-10-07 | 166.07 | 22.84 | 103 | 85.91 | 30 | 300 | OK | 28.64%
TK-501 | Jet A-1 | Product | 8 | 2026-10-08 | 85.91 | 23.3 | 18 | 91.21 | 30 | 300 | OK | 30.4%
TK-501 | Jet A-1 | Product | 9 | 2026-10-09 | 91.21 | 23.32 | 18 | 96.53 | 30 | 300 | OK | 32.18%
TK-501 | Jet A-1 | Product | 10 | 2026-10-10 | 96.53 | 23.3 | 18 | 101.83 | 30 | 300 | OK | 33.94%
TK-501 | Jet A-1 | Product | 11 | 2026-10-11 | 101.83 | 23.3 | 18 | 107.13 | 30 | 300 | OK | 35.71%
TK-501 | Jet A-1 | Product | 12 | 2026-10-12 | 107.13 | 23.3 | 18 | 112.43 | 30 | 300 | OK | 37.48%
TK-501 | Jet A-1 | Product | 13 | 2026-10-13 | 112.43 | 23.3 | 18 | 117.73 | 30 | 300 | OK | 39.24%
TK-501 | Jet A-1 | Product | 14 | 2026-10-14 | 117.73 | 23.3 | 18 | 123.03 | 30 | 300 | OK | 41.01%
TK-501 | Jet A-1 | Product | 15 | 2026-10-15 | 123.03 | 23.3 | 18 | 128.33 | 30 | 300 | OK | 42.78%
TK-501 | Jet A-1 | Product | 16 | 2026-10-16 | 128.33 | 23.3 | 18 | 133.63 | 30 | 300 | OK | 44.54%
TK-501 | Jet A-1 | Product | 17 | 2026-10-17 | 133.63 | 23.3 | 18 | 138.93 | 30 | 300 | OK | 46.31%
TK-501 | Jet A-1 | Product | 18 | 2026-10-18 | 138.93 | 23.3 | 18 | 144.23 | 30 | 300 | OK | 48.08%
TK-501 | Jet A-1 | Product | 19 | 2026-10-19 | 144.23 | 23.3 | 18 | 149.53 | 30 | 300 | OK | 49.84%
TK-501 | Jet A-1 | Product | 20 | 2026-10-20 | 149.53 | 23.3 | 18 | 154.83 | 30 | 300 | OK | 51.61%
TK-501 | Jet A-1 | Product | 21 | 2026-10-21 | 154.83 | 23.3 | 103 | 75.13 | 30 | 300 | OK | 25.04%
TK-501 | Jet A-1 | Product | 22 | 2026-10-22 | 75.13 | 23.3 | 18 | 80.43 | 30 | 300 | OK | 26.81%
TK-501 | Jet A-1 | Product | 23 | 2026-10-23 | 80.43 | 23.3 | 18 | 85.73 | 30 | 300 | OK | 28.58%
TK-501 | Jet A-1 | Product | 24 | 2026-10-24 | 85.73 | 23.3 | 18 | 91.03 | 30 | 300 | OK | 30.34%
TK-501 | Jet A-1 | Product | 25 | 2026-10-25 | 91.03 | 23.3 | 18 | 96.33 | 30 | 300 | OK | 32.11%
TK-501 | Jet A-1 | Product | 26 | 2026-10-26 | 96.33 | 23.3 | 18 | 101.63 | 30 | 300 | OK | 33.88%
TK-501 | Jet A-1 | Product | 27 | 2026-10-27 | 101.63 | 23.3 | 18 | 106.93 | 30 | 300 | OK | 35.64%
TK-501 | Jet A-1 | Product | 28 | 2026-10-28 | 106.93 | 23.3 | 18 | 112.23 | 30 | 300 | OK | 37.41%
TK-501 | Jet A-1 | Product | 29 | 2026-10-29 | 112.23 | 23.3 | 18 | 117.53 | 30 | 300 | OK | 39.18%
TK-501 | Jet A-1 | Product | 30 | 2026-10-30 | 117.53 | 23.3 | 18 | 122.83 | 30 | 300 | OK | 40.94%
TK-501 | Jet A-1 | Product | 31 | 2026-10-31 | 122.83 | 23.3 | 18 | 128.13 | 30 | 300 | OK | 42.71%
TK-601 | Diesel B10 | Product | 1 | 2026-10-01 | 230 | 43.2768 | 35 | 238.2768 | 50 | 500 | OK | 47.66%
TK-601 | Diesel B10 | Product | 2 | 2026-10-02 | 238.2768 | 43.2768 | 35 | 246.5536 | 50 | 500 | OK | 49.31%
TK-601 | Diesel B10 | Product | 3 | 2026-10-03 | 246.5536 | 43.512 | 35 | 255.0656 | 50 | 500 | OK | 51.01%
TK-601 | Diesel B10 | Product | 4 | 2026-10-04 | 255.0656 | 40.9444 | 35 | 261.01 | 50 | 500 | OK | 52.2%
TK-601 | Diesel B10 | Product | 5 | 2026-10-05 | 261.01 | 38.1612 | 35 | 264.1712 | 50 | 500 | OK | 52.83%
TK-601 | Diesel B10 | Product | 6 | 2026-10-06 | 264.1712 | 40.2584 | 35 | 269.4296 | 50 | 500 | OK | 53.89%
TK-601 | Diesel B10 | Product | 7 | 2026-10-07 | 269.4296 | 42.6496 | 35 | 277.0792 | 50 | 500 | OK | 55.42%
TK-601 | Diesel B10 | Product | 8 | 2026-10-08 | 277.0792 | 43.4532 | 35 | 285.5324 | 50 | 500 | OK | 57.11%
TK-601 | Diesel B10 | Product | 9 | 2026-10-09 | 285.5324 | 43.4336 | 35 | 293.966 | 50 | 500 | OK | 58.79%
TK-601 | Diesel B10 | Product | 10 | 2026-10-10 | 293.966 | 43.2768 | 35 | 302.2428 | 50 | 500 | OK | 60.45%
TK-601 | Diesel B10 | Product | 11 | 2026-10-11 | 302.2428 | 43.2768 | 175 | 170.5196 | 50 | 500 | OK | 34.1%
TK-601 | Diesel B10 | Product | 12 | 2026-10-12 | 170.5196 | 43.2768 | 35 | 178.7964 | 50 | 500 | OK | 35.76%
TK-601 | Diesel B10 | Product | 13 | 2026-10-13 | 178.7964 | 43.2768 | 35 | 187.0732 | 50 | 500 | OK | 37.41%
TK-601 | Diesel B10 | Product | 14 | 2026-10-14 | 187.0732 | 43.2768 | 35 | 195.35 | 50 | 500 | OK | 39.07%
TK-601 | Diesel B10 | Product | 15 | 2026-10-15 | 195.35 | 43.2768 | 35 | 203.6268 | 50 | 500 | OK | 40.73%
TK-601 | Diesel B10 | Product | 16 | 2026-10-16 | 203.6268 | 43.2768 | 35 | 211.9036 | 50 | 500 | OK | 42.38%
TK-601 | Diesel B10 | Product | 17 | 2026-10-17 | 211.9036 | 43.2768 | 35 | 220.1804 | 50 | 500 | OK | 44.04%
TK-601 | Diesel B10 | Product | 18 | 2026-10-18 | 220.1804 | 43.2768 | 35 | 228.4572 | 50 | 500 | OK | 45.69%
TK-601 | Diesel B10 | Product | 19 | 2026-10-19 | 228.4572 | 43.2768 | 35 | 236.734 | 50 | 500 | OK | 47.35%
TK-601 | Diesel B10 | Product | 20 | 2026-10-20 | 236.734 | 43.2768 | 35 | 245.0108 | 50 | 500 | OK | 49%
TK-601 | Diesel B10 | Product | 21 | 2026-10-21 | 245.0108 | 43.2768 | 35 | 253.2876 | 50 | 500 | OK | 50.66%
TK-601 | Diesel B10 | Product | 22 | 2026-10-22 | 253.2876 | 43.2768 | 35 | 261.5644 | 50 | 500 | OK | 52.31%
TK-601 | Diesel B10 | Product | 23 | 2026-10-23 | 261.5644 | 43.2768 | 35 | 269.8412 | 50 | 500 | OK | 53.97%
TK-601 | Diesel B10 | Product | 24 | 2026-10-24 | 269.8412 | 43.2768 | 35 | 278.118 | 50 | 500 | OK | 55.62%
TK-601 | Diesel B10 | Product | 25 | 2026-10-25 | 278.118 | 43.2768 | 175 | 146.3948 | 50 | 500 | OK | 29.28%
TK-601 | Diesel B10 | Product | 26 | 2026-10-26 | 146.3948 | 43.2768 | 35 | 154.6716 | 50 | 500 | OK | 30.93%
TK-601 | Diesel B10 | Product | 27 | 2026-10-27 | 154.6716 | 43.2768 | 35 | 162.9484 | 50 | 500 | OK | 32.59%
TK-601 | Diesel B10 | Product | 28 | 2026-10-28 | 162.9484 | 43.2768 | 35 | 171.2252 | 50 | 500 | OK | 34.25%
TK-601 | Diesel B10 | Product | 29 | 2026-10-29 | 171.2252 | 43.2768 | 35 | 179.502 | 50 | 500 | OK | 35.9%
TK-601 | Diesel B10 | Product | 30 | 2026-10-30 | 179.502 | 43.2768 | 35 | 187.7788 | 50 | 500 | OK | 37.56%
TK-601 | Diesel B10 | Product | 31 | 2026-10-31 | 187.7788 | 43.2768 | 35 | 196.0556 | 50 | 500 | OK | 39.21%
TK-701 | Fuel Oil | Product | 1 | 2026-10-01 | 180 | 21.32 | 0 | 201.32 | 40 | 400 | OK | 50.33%
TK-701 | Fuel Oil | Product | 2 | 2026-10-02 | 201.32 | 21.32 | 0 | 222.64 | 40 | 400 | OK | 55.66%
TK-701 | Fuel Oil | Product | 3 | 2026-10-03 | 222.64 | 20.42 | 0 | 243.06 | 40 | 400 | OK | 60.76%
TK-701 | Fuel Oil | Product | 4 | 2026-10-04 | 243.06 | 20.52 | 0 | 263.58 | 40 | 400 | OK | 65.89%
TK-701 | Fuel Oil | Product | 5 | 2026-10-05 | 263.58 | 18.78 | 0 | 282.36 | 40 | 400 | OK | 70.59%
TK-701 | Fuel Oil | Product | 6 | 2026-10-06 | 282.36 | 19.35 | 200 | 101.71 | 40 | 400 | OK | 25.43%
TK-701 | Fuel Oil | Product | 7 | 2026-10-07 | 101.71 | 20.19 | 0 | 121.9 | 40 | 400 | OK | 30.48%
TK-701 | Fuel Oil | Product | 8 | 2026-10-08 | 121.9 | 20.38 | 0 | 142.28 | 40 | 400 | OK | 35.57%
TK-701 | Fuel Oil | Product | 9 | 2026-10-09 | 142.28 | 20.35 | 0 | 162.63 | 40 | 400 | OK | 40.66%
TK-701 | Fuel Oil | Product | 10 | 2026-10-10 | 162.63 | 21.32 | 0 | 183.95 | 40 | 400 | OK | 45.99%
TK-701 | Fuel Oil | Product | 11 | 2026-10-11 | 183.95 | 21.32 | 0 | 205.27 | 40 | 400 | OK | 51.32%
TK-701 | Fuel Oil | Product | 12 | 2026-10-12 | 205.27 | 21.32 | 0 | 226.59 | 40 | 400 | OK | 56.65%
TK-701 | Fuel Oil | Product | 13 | 2026-10-13 | 226.59 | 21.32 | 0 | 247.91 | 40 | 400 | OK | 61.98%
TK-701 | Fuel Oil | Product | 14 | 2026-10-14 | 247.91 | 21.32 | 0 | 269.23 | 40 | 400 | OK | 67.31%
TK-701 | Fuel Oil | Product | 15 | 2026-10-15 | 269.23 | 21.32 | 0 | 290.55 | 40 | 400 | OK | 72.64%
TK-701 | Fuel Oil | Product | 16 | 2026-10-16 | 290.55 | 21.32 | 0 | 311.87 | 40 | 400 | OK | 77.97%
TK-701 | Fuel Oil | Product | 17 | 2026-10-17 | 311.87 | 21.32 | 0 | 333.19 | 40 | 400 | OK | 83.3%
TK-701 | Fuel Oil | Product | 18 | 2026-10-18 | 333.19 | 21.32 | 200 | 154.51 | 40 | 400 | OK | 38.63%
TK-701 | Fuel Oil | Product | 19 | 2026-10-19 | 154.51 | 21.32 | 0 | 175.83 | 40 | 400 | OK | 43.96%
TK-701 | Fuel Oil | Product | 20 | 2026-10-20 | 175.83 | 21.32 | 0 | 197.15 | 40 | 400 | OK | 49.29%
TK-701 | Fuel Oil | Product | 21 | 2026-10-21 | 197.15 | 21.32 | 0 | 218.47 | 40 | 400 | OK | 54.62%
TK-701 | Fuel Oil | Product | 22 | 2026-10-22 | 218.47 | 21.32 | 0 | 239.79 | 40 | 400 | OK | 59.95%
TK-701 | Fuel Oil | Product | 23 | 2026-10-23 | 239.79 | 21.32 | 0 | 261.11 | 40 | 400 | OK | 65.28%
TK-701 | Fuel Oil | Product | 24 | 2026-10-24 | 261.11 | 21.32 | 0 | 282.43 | 40 | 400 | OK | 70.61%
TK-701 | Fuel Oil | Product | 25 | 2026-10-25 | 282.43 | 21.32 | 0 | 303.75 | 40 | 400 | OK | 75.94%
TK-701 | Fuel Oil | Product | 26 | 2026-10-26 | 303.75 | 21.32 | 0 | 325.07 | 40 | 400 | OK | 81.27%
TK-701 | Fuel Oil | Product | 27 | 2026-10-27 | 325.07 | 21.32 | 0 | 346.39 | 40 | 400 | OK | 86.6%
TK-701 | Fuel Oil | Product | 28 | 2026-10-28 | 346.39 | 21.32 | 0 | 367.71 | 40 | 400 | OK | 91.93%
TK-701 | Fuel Oil | Product | 29 | 2026-10-29 | 367.71 | 21.32 | 200 | 189.03 | 40 | 400 | OK | 47.26%
TK-701 | Fuel Oil | Product | 30 | 2026-10-30 | 189.03 | 21.32 | 0 | 210.35 | 40 | 400 | OK | 52.59%
TK-701 | Fuel Oil | Product | 31 | 2026-10-31 | 210.35 | 21.32 | 0 | 231.67 | 40 | 400 | OK | 57.92%

## Tank_Summary
Tank Inventory Overview – closing inventory (kbbl) and fill %
Wide view of Tank_Balance for quick visual checks. All values are links.
|  | Closing inventory (kbbl) | [9 empty] | Fill % of working capacity
Day | Date | TK-101 Arab Light | TK-102 Murban | TK-103 Tapis | TK-104 Kimanis | TK-201 LPG | TK-301 Naphtha | TK-401 Gasoline 95 | TK-501 Jet A-1 | TK-601 Diesel B10 | TK-701 Fuel Oil | TK-101 Arab Light | TK-102 Murban | TK-103 Tapis | TK-104 Kimanis | TK-201 LPG | TK-301 Naphtha | TK-401 Gasoline 95 | TK-501 Jet A-1 | TK-601 Diesel B10 | TK-701 Fuel Oil
1 | 2026-10-01 | 660 | 460 | 410 | 350 | 32.32 | 119.6 | 185.12 | 145.3 | 238.2768 | 201.32 | 44% | 46% | 45.56% | 43.75% | 53.87% | 47.84% | 46.28% | 48.43% | 47.66% | 50.33%
2 | 2026-10-02 | 620 | 420 | 370 | 320 | 34.64 | 129.2 | 190.24 | 150.6 | 246.5536 | 222.64 | 41.33% | 42% | 41.11% | 40% | 57.73% | 51.68% | 47.56% | 50.2% | 49.31% | 55.66%
3 | 2026-10-03 | 579 | 382 | 329 | 290 | 37.21 | 137.72 | 196.72 | 155.89 | 255.0656 | 243.06 | 38.6% | 38.2% | 36.56% | 36.25% | 62.02% | 55.09% | 49.18% | 51.96% | 51.01% | 60.76%
4 | 2026-10-04 | 540 | 346 | 290 | 262 | 38.88 | 146.56 | 199.96 | 159.94 | 261.01 | 263.58 | 36% | 34.6% | 32.22% | 32.75% | 64.8% | 58.62% | 49.99% | 53.31% | 52.2% | 65.89%
5 | 2026-10-05 | 505 | 812 | 253 | 236 | 39.79 | 155.36 | 200.48 | 162.47 | 264.1712 | 282.36 | 33.67% | 81.2% | 28.11% | 29.5% | 66.32% | 62.14% | 50.12% | 54.16% | 52.83% | 70.59%
6 | 2026-10-06 | 468 | 776 | 615 | 208 | 41.31 | 164.62 | 202.88 | 166.07 | 269.4296 | 101.71 | 31.2% | 77.6% | 68.33% | 26% | 68.85% | 65.85% | 50.72% | 55.36% | 53.89% | 25.43%
7 | 2026-10-07 | 429 | 738 | 575 | 178 | 43.55 | 173.56 | 208 | 85.91 | 277.0792 | 121.9 | 28.6% | 73.8% | 63.89% | 22.25% | 72.58% | 69.42% | 52% | 28.64% | 55.42% | 30.48%
8 | 2026-10-08 | 989 | 698 | 535 | 148 | 46.05 | 183.16 | 213.64 | 91.21 | 285.5324 | 142.28 | 65.93% | 69.8% | 59.44% | 18.5% | 76.75% | 73.26% | 53.41% | 30.4% | 57.11% | 35.57%
9 | 2026-10-09 | 949 | 658 | 494 | 119 | 48.64 | 91.78 | 220.12 | 96.53 | 293.966 | 162.63 | 63.27% | 65.8% | 54.89% | 14.88% | 81.07% | 36.71% | 55.03% | 32.18% | 58.79% | 40.66%
10 | 2026-10-10 | 909 | 618 | 454 | 439 | 20.96 | 101.38 | 225.24 | 101.83 | 302.2428 | 183.95 | 60.6% | 61.8% | 50.44% | 54.87% | 34.93% | 40.55% | 56.31% | 33.94% | 60.45% | 45.99%
11 | 2026-10-11 | 869 | 578 | 414 | 409 | 23.28 | 110.98 | 230.36 | 107.13 | 170.5196 | 205.27 | 57.93% | 57.8% | 46% | 51.12% | 38.8% | 44.39% | 57.59% | 35.71% | 34.1% | 51.32%
12 | 2026-10-12 | 829 | 538 | 374 | 379 | 25.6 | 120.58 | 155.48 | 112.43 | 178.7964 | 226.59 | 55.27% | 53.8% | 41.56% | 47.38% | 42.67% | 48.23% | 38.87% | 37.48% | 35.76% | 56.65%
13 | 2026-10-13 | 789 | 498 | 334 | 349 | 27.92 | 130.18 | 160.6 | 117.73 | 187.0732 | 247.91 | 52.6% | 49.8% | 37.11% | 43.62% | 46.53% | 52.07% | 40.15% | 39.24% | 37.41% | 61.98%
14 | 2026-10-14 | 749 | 458 | 294 | 319 | 30.24 | 139.78 | 165.72 | 123.03 | 195.35 | 269.23 | 49.93% | 45.8% | 32.67% | 39.88% | 50.4% | 55.91% | 41.43% | 41.01% | 39.07% | 67.31%
15 | 2026-10-15 | 709 | 418 | 254 | 289 | 32.56 | 149.38 | 170.84 | 128.33 | 203.6268 | 290.55 | 47.27% | 41.8% | 28.22% | 36.12% | 54.27% | 59.75% | 42.71% | 42.78% | 40.73% | 72.64%
16 | 2026-10-16 | 669 | 378 | 614 | 259 | 34.88 | 158.98 | 175.96 | 133.63 | 211.9036 | 311.87 | 44.6% | 37.8% | 68.22% | 32.38% | 58.13% | 63.59% | 43.99% | 44.54% | 42.38% | 77.97%
17 | 2026-10-17 | 629 | 338 | 574 | 229 | 37.2 | 168.58 | 181.08 | 138.93 | 220.1804 | 333.19 | 41.93% | 33.8% | 63.78% | 28.62% | 62% | 67.43% | 45.27% | 46.31% | 44.04% | 83.3%
18 | 2026-10-18 | 589 | 298 | 534 | 199 | 39.52 | 178.18 | 186.2 | 144.23 | 228.4572 | 154.51 | 39.27% | 29.8% | 59.33% | 24.88% | 65.87% | 71.27% | 46.55% | 48.08% | 45.69% | 38.63%
19 | 2026-10-19 | 549 | 758 | 494 | 169 | 41.84 | 187.78 | 191.32 | 149.53 | 236.734 | 175.83 | 36.6% | 75.8% | 54.89% | 21.12% | 69.73% | 75.11% | 47.83% | 49.84% | 47.35% | 43.96%
20 | 2026-10-20 | 509 | 718 | 454 | 139 | 44.16 | 97.38 | 196.44 | 154.83 | 245.0108 | 197.15 | 33.93% | 71.8% | 50.44% | 17.38% | 73.6% | 38.95% | 49.11% | 51.61% | 49% | 49.29%
21 | 2026-10-21 | 469 | 678 | 414 | 109 | 46.48 | 106.98 | 201.56 | 75.13 | 253.2876 | 218.47 | 31.27% | 67.8% | 46% | 13.63% | 77.47% | 42.79% | 50.39% | 25.04% | 50.66% | 54.62%
22 | 2026-10-22 | 929 | 638 | 374 | 429 | 48.8 | 116.58 | 206.68 | 80.43 | 261.5644 | 239.79 | 61.93% | 63.8% | 41.56% | 53.62% | 81.33% | 46.63% | 51.67% | 26.81% | 52.31% | 59.95%
23 | 2026-10-23 | 889 | 598 | 334 | 399 | 51.12 | 126.18 | 211.8 | 85.73 | 269.8412 | 261.11 | 59.27% | 59.8% | 37.11% | 49.88% | 85.2% | 50.47% | 52.95% | 28.58% | 53.97% | 65.28%
24 | 2026-10-24 | 849 | 558 | 294 | 369 | 23.44 | 135.78 | 216.92 | 91.03 | 278.118 | 282.43 | 56.6% | 55.8% | 32.67% | 46.12% | 39.07% | 54.31% | 54.23% | 30.34% | 55.62% | 70.61%
25 | 2026-10-25 | 809 | 518 | 254 | 339 | 25.76 | 145.38 | 222.04 | 96.33 | 146.3948 | 303.75 | 53.93% | 51.8% | 28.22% | 42.38% | 42.93% | 58.15% | 55.51% | 32.11% | 29.28% | 75.94%
26 | 2026-10-26 | 769 | 478 | 614 | 309 | 28.08 | 154.98 | 147.16 | 101.63 | 154.6716 | 325.07 | 51.27% | 47.8% | 68.22% | 38.62% | 46.8% | 61.99% | 36.79% | 33.88% | 30.93% | 81.27%
27 | 2026-10-27 | 729 | 438 | 574 | 279 | 30.4 | 164.58 | 152.28 | 106.93 | 162.9484 | 346.39 | 48.6% | 43.8% | 63.78% | 34.88% | 50.67% | 65.83% | 38.07% | 35.64% | 32.59% | 86.6%
28 | 2026-10-28 | 689 | 398 | 534 | 249 | 32.72 | 174.18 | 157.4 | 112.23 | 171.2252 | 367.71 | 45.93% | 39.8% | 59.33% | 31.13% | 54.53% | 69.67% | 39.35% | 37.41% | 34.25% | 91.93%
29 | 2026-10-29 | 649 | 358 | 494 | 219 | 35.04 | 183.78 | 162.52 | 117.53 | 179.502 | 189.03 | 43.27% | 35.8% | 54.89% | 27.38% | 58.4% | 73.51% | 40.63% | 39.18% | 35.9% | 47.26%
30 | 2026-10-30 | 609 | 318 | 454 | 189 | 37.36 | 93.38 | 167.64 | 122.83 | 187.7788 | 210.35 | 40.6% | 31.8% | 50.44% | 23.62% | 62.27% | 37.35% | 41.91% | 40.94% | 37.56% | 52.59%
31 | 2026-10-31 | 569 | 278 | 414 | 159 | 39.68 | 102.98 | 172.76 | 128.13 | 196.0556 | 231.67 | 37.93% | 27.8% | 46% | 19.88% | 66.13% | 41.19% | 43.19% | 42.71% | 39.21% | 57.92%

## Constraint_Check
Constraint Check – does the current plan satisfy every plant constraint?
Re-evaluates automatically when the optimizer writes new decision variables into Daily_Plan. VIOL = constraint breached.
Day | Date | Status | CDU rate | C1 CDU cap | Crude max | C2 Crude rate | CDU Δ vs prev day | C3 Ramp | Reformer feed | C4 Ref cap | C5 Naph avail | RFCC feed | C6 RFCC cap | C7 Resid avail | DHT feed | C8 DHT cap | Gasoline RON | C9 RON spec | Residue S wt% | C10 Sulfur | Tank breaches | C13 Tank limits | Day result
1 | 2026-10-01 | Actual | 150 | OK | 0 | OK | n/a | n/a | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
2 | 2026-10-02 | Actual | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
3 | 2026-10-03 | Actual | 150 | OK | 0 | OK | 0 | OK | 23 | OK | OK | 33 | OK | OK | 44.4 | OK | 95.1776 | OK | 1.4698 | OK | 0 | OK | FEASIBLE
4 | 2026-10-04 | Actual | 142 | OK | 0 | OK | -8 | OK | 21 | OK | OK | 30 | OK | OK | 41.78 | OK | 95.1841 | OK | 1.4742 | OK | 0 | OK | FEASIBLE
5 | 2026-10-05 | Actual | 132 | OK | 0 | OK | -10 | OK | 19 | OK | OK | 28 | OK | OK | 38.94 | OK | 95.1376 | OK | 1.4487 | OK | 0 | OK | FEASIBLE
6 | 2026-10-06 | Actual | 139 | OK | 0 | OK | 7 | OK | 20 | OK | OK | 30 | OK | OK | 41.08 | OK | 95.1111 | OK | 1.4528 | OK | 0 | OK | FEASIBLE
7 | 2026-10-07 | Actual | 147 | OK | 0 | OK | 8 | OK | 22 | OK | OK | 32 | OK | OK | 43.52 | OK | 95.1572 | OK | 1.4495 | OK | 0 | OK | FEASIBLE
8 | 2026-10-08 | Actual | 150 | OK | 0 | OK | 3 | OK | 22 | OK | OK | 33 | OK | OK | 44.34 | OK | 95.1111 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
9 | 2026-10-09 | Actual | 150 | OK | 0 | OK | 0 | OK | 23 | OK | OK | 33 | OK | OK | 44.32 | OK | 95.1776 | OK | 1.4616 | OK | 0 | OK | FEASIBLE
10 | 2026-10-10 | Actual | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
11 | 2026-10-11 | Actual | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
12 | 2026-10-12 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
13 | 2026-10-13 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
14 | 2026-10-14 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
15 | 2026-10-15 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
16 | 2026-10-16 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
17 | 2026-10-17 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
18 | 2026-10-18 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
19 | 2026-10-19 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
20 | 2026-10-20 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
21 | 2026-10-21 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
22 | 2026-10-22 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
23 | 2026-10-23 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
24 | 2026-10-24 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
25 | 2026-10-25 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
26 | 2026-10-26 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
27 | 2026-10-27 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
28 | 2026-10-28 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
29 | 2026-10-29 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
30 | 2026-10-30 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
31 | 2026-10-31 | Plan | 150 | OK | 0 | OK | 0 | OK | 22 | OK | OK | 32 | OK | OK | 44.16 | OK | 95.1572 | OK | 1.4611 | OK | 0 | OK | FEASIBLE
Violations |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
C14 – End-of-month inventory targets (closing 31-Oct ≥ target)
Tank ID | Service | Closing 31-Oct | Target | C14 Check
TK-101 | Arab Light | 569 | 400 | OK
TK-102 | Murban | 278 | 250 | OK
TK-103 | Tapis | 414 | 250 | OK
TK-104 | Kimanis | 159 | 150 | OK
TK-201 | LPG | 39.68 | 20 | OK
TK-301 | Naphtha | 102.98 | 50 | OK
TK-401 | Gasoline 95 | 172.76 | 150 | OK
TK-501 | Jet A-1 | 128.13 | 100 | OK
TK-601 | Diesel B10 | 196.0556 | 180 | OK
TK-701 | Fuel Oil | 231.67 | 100 | OK
C14 violations |  |  |  | 0
Note on X37: Total violations across all days + C14. Must be 0 for a feasible plan.

## Crude_Data
Crude Slate & Assay Data
Illustrative assay/price values for optimizer testing only – replace with site assay (LIMS/crude assay library) and current price deck.
Property | Unit | Arab Light | Murban | Tapis | Kimanis
Crude price (delivered) | $/bbl | 76 | 80.5 | 84 | 82.5
Yield – LPG | vol frac | 0.02 | 0.03 | 0.03 | 0.02
Yield – SR Naphtha | vol frac | 0.18 | 0.24 | 0.22 | 0.2
Yield – Kerosene | vol frac | 0.14 | 0.16 | 0.17 | 0.15
Yield – SR Gasoil | vol frac | 0.2 | 0.22 | 0.3 | 0.32
Yield – Atm Residue | vol frac | 0.45 | 0.34 | 0.27 | 0.3
Yield – Loss / fuel | vol frac | 0.01 | 0.01 | 0.01 | 0.01
Yield closure check (must = 1.000) | vol frac | 1 | 1 | 1 | 1
Atm Residue sulfur | wt% | 3 | 1.3 | 0.15 | 0.2
Max CDU feed rate | kbbl/d | 60 | 50 | 50 | 40
Min CDU feed rate | kbbl/d | 0 | 0 | 0 | 0
Storage tank | - | TK-101 | TK-102 | TK-103 | TK-104
Notes
• Yields are fixed CDU cut yields (vol) – linear model, no cut-point or severity optimisation.
• Max CDU rate per crude reflects handling limits (e.g. waxy Kimanis, sour Arab Light corrosion window).
• Residue sulfur is used in the residue-pool sulfur constraint (C10) – volumetric blending approximation.

## Unit_Data
Process Unit Constraints, Yields & Operating Cost
Blue = editable parameter. Row numbers are referenced by formulas in Daily_Plan and Constraint_Check – do not insert rows.
Unit | Parameter | Unit of measure | Value | Comment
CDU | Max throughput | kbbl/d | 150 | Nameplate crude distillation capacity
CDU | Min throughput (turndown) | kbbl/d | 100 | Furnace / column hydraulic turndown
CDU | Max day-to-day rate change | kbbl/d | 10 | Ramp limit for stable operation
CDU | Variable opex | $/bbl feed | 1 | Fuel, power, chemicals
Reformer | Max feed | kbbl/d | 25 | CCR / semi-regen capacity
Reformer | Min feed | kbbl/d | 10 | Min stable feed
Reformer | Variable opex | $/bbl feed | 2.5 | Incl. catalyst & utilities
Reformer | Yield – Reformate | vol frac | 0.84
Reformer | Yield – LPG | vol frac | 0.08
Reformer | Yield – H2 / fuel gas (calc) | vol frac | 0.08 | Balance to 1.0 – consumed internally
RFCC | Max feed | kbbl/d | 35 | Residue FCC capacity
RFCC | Min feed | kbbl/d | 15 | Min stable feed
RFCC | Variable opex | $/bbl feed | 4 | Catalyst, utilities
RFCC | Yield – FCC gasoline | vol frac | 0.52
RFCC | Yield – LPG | vol frac | 0.18
RFCC | Yield – LCO | vol frac | 0.18 | Sent to DHT
RFCC | Yield – Slurry | vol frac | 0.06 | Blended to fuel oil
RFCC | Yield – Coke / dry gas (calc) | vol frac | 0.06 | Balance to 1.0
DHT | Max feed | kbbl/d | 48 | Diesel hydrotreater capacity
DHT | Min feed | kbbl/d | 20 | Min stable feed
DHT | Variable opex | $/bbl feed | 1.5 | H2, utilities
DHT | Yield – Diesel | vol frac | 0.98
Blending | RON – Reformate | RON | 98
Blending | RON – FCC gasoline | RON | 92
Blending | Gasoline pool RON min spec | RON | 95 | Product spec (Gasoline 95)
Blending | Atm residue pool sulfur max | wt% | 1.5 | RFCC feed / fuel oil sulfur limit

## Product_Data
Product Prices & Tankage Mapping
Illustrative product netbacks for optimizer testing – replace with current price deck.
Property | Unit | LPG | Naphtha | Gasoline 95 | Jet A-1 | Diesel B10 | Fuel Oil
Product price (netback) | $/bbl | 60 | 74 | 99 | 103 | 105 | 72
Storage tank | - | TK-201 | TK-301 | TK-401 | TK-501 | TK-601 | TK-701
Produced from | - | SR LPG + Reformer LPG + RFCC LPG | SR Naphtha not sent to Reformer | Reformate + FCC gasoline | Kerosene (Merox) | DHT product (SR gasoil + LCO) | Unconverted residue + slurry

## Tank_Master
Tank Master Data
Inventories in kbbl. Opening = start of 1-Oct-2026. End target applies to closing inventory on 31-Oct-2026 (constraint C14).
Tank ID | Service | Type | Working capacity (kbbl) | Min heel (kbbl) | Opening inv. 1-Oct (kbbl) | End-of-month min target (kbbl) | Notes
TK-101 | Arab Light | Crude | 1500 | 150 | 700 | 400 | Tank group (aggregated)
TK-102 | Murban | Crude | 1000 | 100 | 500 | 250 | Tank group (aggregated)
TK-103 | Tapis | Crude | 900 | 90 | 450 | 250 | Tank group (aggregated)
TK-104 | Kimanis | Crude | 800 | 80 | 380 | 150 | Tank group (aggregated)
TK-201 | LPG | Product | 60 | 6 | 30 | 20 | Product rundown + finished tank
TK-301 | Naphtha | Product | 250 | 25 | 110 | 50 | Product rundown + finished tank
TK-401 | Gasoline 95 | Product | 400 | 40 | 180 | 150 | Product rundown + finished tank
TK-501 | Jet A-1 | Product | 300 | 30 | 140 | 100 | Product rundown + finished tank
TK-601 | Diesel B10 | Product | 500 | 50 | 230 | 180 | Product rundown + finished tank
TK-701 | Fuel Oil | Product | 400 | 40 | 180 | 100 | Product rundown + finished tank

## Crude_Receipts
Crude Receipt Schedule (kbbl)
Fixed cargo arrivals into crude tanks (parameter, not a decision variable).
Day | Date | Arab Light | Murban | Tapis | Kimanis
1 | 2026-10-01 | 0 | 0 | 0 | 0
2 | 2026-10-02 | 0 | 0 | 0 | 0
3 | 2026-10-03 | 0 | 0 | 0 | 0
4 | 2026-10-04 | 0 | 0 | 0 | 0
5 | 2026-10-05 | 0 | 500 | 0 | 0
6 | 2026-10-06 | 0 | 0 | 400 | 0
7 | 2026-10-07 | 0 | 0 | 0 | 0
8 | 2026-10-08 | 600 | 0 | 0 | 0
9 | 2026-10-09 | 0 | 0 | 0 | 0
10 | 2026-10-10 | 0 | 0 | 0 | 350
11 | 2026-10-11 | 0 | 0 | 0 | 0
12 | 2026-10-12 | 0 | 0 | 0 | 0
13 | 2026-10-13 | 0 | 0 | 0 | 0
14 | 2026-10-14 | 0 | 0 | 0 | 0
15 | 2026-10-15 | 0 | 0 | 0 | 0
16 | 2026-10-16 | 0 | 0 | 400 | 0
17 | 2026-10-17 | 0 | 0 | 0 | 0
18 | 2026-10-18 | 0 | 0 | 0 | 0
19 | 2026-10-19 | 0 | 500 | 0 | 0
20 | 2026-10-20 | 0 | 0 | 0 | 0
21 | 2026-10-21 | 0 | 0 | 0 | 0
22 | 2026-10-22 | 500 | 0 | 0 | 350
23 | 2026-10-23 | 0 | 0 | 0 | 0
24 | 2026-10-24 | 0 | 0 | 0 | 0
25 | 2026-10-25 | 0 | 0 | 0 | 0
26 | 2026-10-26 | 0 | 0 | 400 | 0
27 | 2026-10-27 | 0 | 0 | 0 | 0
28 | 2026-10-28 | 0 | 0 | 0 | 0
29 | 2026-10-29 | 0 | 0 | 0 | 0
30 | 2026-10-30 | 0 | 0 | 0 | 0
31 | 2026-10-31 | 0 | 0 | 0 | 0
Total |  | 1100 | 1000 | 1200 | 700

## Product_Liftings
Product Lifting Schedule (kbbl)
Daily pipeline/truck liftings plus vessel cargoes (parameter, not a decision variable).
Day | Date | LPG | Naphtha | Gasoline 95 | Jet A-1 | Diesel B10 | Fuel Oil
1 | 2026-10-01 | 9 | 0 | 30 | 18 | 35 | 0
2 | 2026-10-02 | 9 | 0 | 30 | 18 | 35 | 0
3 | 2026-10-03 | 9 | 0 | 30 | 18 | 35 | 0
4 | 2026-10-04 | 9 | 0 | 30 | 18 | 35 | 0
5 | 2026-10-05 | 9 | 0 | 30 | 18 | 35 | 0
6 | 2026-10-06 | 9 | 0 | 30 | 18 | 35 | 200
7 | 2026-10-07 | 9 | 0 | 30 | 103 | 35 | 0
8 | 2026-10-08 | 9 | 0 | 30 | 18 | 35 | 0
9 | 2026-10-09 | 9 | 100 | 30 | 18 | 35 | 0
10 | 2026-10-10 | 39 | 0 | 30 | 18 | 35 | 0
11 | 2026-10-11 | 9 | 0 | 30 | 18 | 175 | 0
12 | 2026-10-12 | 9 | 0 | 110 | 18 | 35 | 0
13 | 2026-10-13 | 9 | 0 | 30 | 18 | 35 | 0
14 | 2026-10-14 | 9 | 0 | 30 | 18 | 35 | 0
15 | 2026-10-15 | 9 | 0 | 30 | 18 | 35 | 0
16 | 2026-10-16 | 9 | 0 | 30 | 18 | 35 | 0
17 | 2026-10-17 | 9 | 0 | 30 | 18 | 35 | 0
18 | 2026-10-18 | 9 | 0 | 30 | 18 | 35 | 200
19 | 2026-10-19 | 9 | 0 | 30 | 18 | 35 | 0
20 | 2026-10-20 | 9 | 100 | 30 | 18 | 35 | 0
21 | 2026-10-21 | 9 | 0 | 30 | 103 | 35 | 0
22 | 2026-10-22 | 9 | 0 | 30 | 18 | 35 | 0
23 | 2026-10-23 | 9 | 0 | 30 | 18 | 35 | 0
24 | 2026-10-24 | 39 | 0 | 30 | 18 | 35 | 0
25 | 2026-10-25 | 9 | 0 | 30 | 18 | 175 | 0
26 | 2026-10-26 | 9 | 0 | 110 | 18 | 35 | 0
27 | 2026-10-27 | 9 | 0 | 30 | 18 | 35 | 0
28 | 2026-10-28 | 9 | 0 | 30 | 18 | 35 | 0
29 | 2026-10-29 | 9 | 0 | 30 | 18 | 35 | 200
30 | 2026-10-30 | 9 | 100 | 30 | 18 | 35 | 0
31 | 2026-10-31 | 9 | 0 | 30 | 18 | 35 | 0
Total |  | 339 | 300 | 1090 | 728 | 1365 | 600